## Stoplight Report
Category | Initiative/Milestone | PJM Contact | MISO Contact | Status
Market Operations | 1) Day Ahead Market Coordination | Mike Ward | Aaron Casto |  | Short-term goals completed. Working on mid-term and long-term goals
| 2) RTO to RTO Data Exchange & Transparency | Rebecca Carroll | Ron Arness |  | Data is posted.
| 3) Stakeholder Education (interchange transactions and CBM) | Rich Souder | Ron Arness |  | Completed. Final draft posted and final discussion took place at October 2012 JCM meeting.
| 4) Interchange Scheduling Business Rule Alignment | Stu Bresler | Dhiman Chatterjee |  | MISO has implemented 20 minute notification period as of October 15, 2013. Per FERC’s direction under Order 764 proceedings, MISO will allow intra-hour schedule changes along with intra-hour settlement process expected to be implemented in 2015. PJM eliminated its minimum 45-minute schedule duration rule on May 19, 2014, in compliance with FERC's orders in the 764 proceeding. PJM and MISO's interchange scheduling processes are therefore now aligned.
| 5) Network External Designated Service - Must Offer Requirement | Stu Bresler | Renuka Chatterjee, Kevin Larson |  | Completed. Refer to PJM RTO stakeholder process.
| 6) Transmission Outage Coordination | Rich Souder | John Harmon |  | MISO and PJM provided an update at January JCM meeting and agreed that the enhanced coordination between FTR groups will further improve PJM's FTR funding. The RTOs have agreed to continue analysis of reasons for short-term flowgate requests and investigate ways to reduce the volume.
| 7) Interchange Optimization | Rebecca Carroll | Dhiman Chatterjee |  | Initial proposal developed and benefit study completed in 2012. MISO and PJM staffs have begun discussions to develop an updated interchange optimization proposal for stakeholder consideration. MISO and PJM are holding joint stakeholder workshops for additional discussion on Interchange Optimization design/solution.
| 8) Interface Pricing | Rebecca Carroll | Dhiman Chatterjee |  | MISO and PJM staff are continuing to evaluate further enhancement and alignment of the methodologies.
| 9) Potential overstatement of external congestion value in Interface Pricing | Rebecca Carroll | Dhiman Chatterjee |  | MISO and PJM staffs are exploring solution options to address the potential interface pricing issue raised by MISO IMM Dr. David Patton. A small stakeholder task force has been formed to explore the issue in more detail.
| 10) Treatment of ONT-ITC PARs in M2M Process | Stan Williams | Ron Arness, Neil Shah |  | MISO and PJM staffs are evaluating options to change the modeling of PARs in the Market Flow calculations and FFE calculations. Stakeholder updates are being provided via the JCM process.
| 11) Freeze Date for Firm Flow Entitlement calcualtions | Rebecca Carroll | Ron Arness, Neil Shah |  | MISO and PJM staffs are discussing options with respect to moving forward from the existing freeze date and providing stakeholder updates via the JCM process.
| 12) FTR Market coordination | Tim Horger | Xiaoming Wang |  | Coordination started in June, 2013. Additional coordination plans will be discussed at future JCM meetings.
| 13) Use of commercial flow in M2M Process | Tim Horger | Ron Arness |  | PJM and MISO are coordinating and identifying impacts of using commercial market flow for M2M accounting. There will be a joint report available for stakeholders at a future JCM meeting. Coordination is also underway with SPP. JOA language changes are anticipated to be developed and presented to stakeholders at a future JCM meeting.
Resource Adequacy | 1) Fact Finding # 1 - Generation Deliverability Testing | Paul McGlynn, Stu Bresler | Vikram Godbole, Jesse Moser, Joe Gardner |  | Coordination on modeling assumptions and building a joint Model -Complete. Fact Finding #1 analysis is ongoing.
| 2) Fact Finding # 2 - Import Capability Testing | Paul McGlynn, Stu Bresler | Digaunto Chatterjee, Jesse Moser, Joe Gardner |  | Completed
| 3) Fact Finding # 3 - Review and Resolution of Issues | Stu Bresler | Joe Gardner |  | On-Target
| 4) Fact Finding # 4 - Document Methodology for cost-benefit analysis | Stu Bresler | Joe Gardner |  | On-Target
| 5) Ensure that RA processes efficiently allocate the existing transmission system for the purposes of cross border capacity transactions. | Stu Bresler | Joe Gardner |  | The workplan to resolve the issues identified/covered at the previous JCM meetings was completed and filed with FERC. Fact finding analysis efforts are currently underway. Efforts on this milestone will begin once the fact finding analysis is completed.
Transmission Planning | 1) Regional Planning Coordination (MTEP/RTEP) | Paul McGlynn | Jesse Moser, Laura Rauch |  | Effort in progress via Order 1000 compliance process and forums - coordinated exchange of models, contingencies and monitored elements, and market efficiency planning including cross-boarder flowgate congestion
| 2) Generation Interconnection and TSR Analysis Timing | Paul McGlynn | Vikram Godbole |  | Presented the proposed BPM language to PJM & MISO stakeholder bodies to document the revised coordination process.
| 3) Market Participant Funded Upgrades/IARR requests | Tim Horger | Laura Rauch |  | An education primer on the MISO process and PJM process for Market Participant Funded Upgrades was presented at the January 24, 2014 JCM meeting.
| 4) Cross Border Planning Projects | Paul McGlynn | Jesse Moser |  | MISO and PJM staff have introduced the issue with stakeholders and will be providing more information in upcoming JCM meetings including a project timeline.
Legend
Completed
On Target -No issues
Monitor - Some Issues
Review - In Jeopardy
On Hold